## GEN Detailed Breakdown
Contract Change Detailed Breakdown |  |  |  | General Contractor Name: |  | ABC General Contractor
State's Project No. | X0000-00 | Description of Change: | [6 empty] | Sheet | 1 of 3
Proposal No. | 1 | Provide (3) 2" conduit for future use. | [6 empty] | Prepared By: | Rep's Name of GC
Date | mm/dd/yy | [7 empty] | Signed By: | Rep of GC
|  |  |  | LABOR |  | MATERIAL |  | EQUIPMENT / OTHER
WORK ITEM |  | QTY | UNIT | Unit Cost | Total | Unit Cost | Total | Unit Cost | Total | SUBTOTAL | REVISIONS
Dig access hole |  | 8 | hour | 80 | 640 |  |  |  |  | 640
Day rental of backhoe |  | 1 | lump |  |  |  |  | 600 | 600 | 600
Backfill hole and remove debris |  | 6 | hour | 55 | 330 |  |  |  |  | 330
Total Direct Costs |  |  |  |  | 970 |  | 0 |  | 600 | 1570
Overhead & Profit |  | 14% | *OH&P% |  | 135.8 |  | 0 |  | 84 | 219.8
[9 empty] | Contractor's Total | 1789.8
SUBCONTRACT COSTS
SUBCONTRACTOR |  | *GC% OH&P |  | Sub Total Direct Costs |  | *GC OH&P | *Sub OH&P |  | Total
Name: SUB Union Electric |  | 3% |  | 1818.6 |  | 54.558 | 254.6 |  | 2127.758
Name: Sub-SUB Coring Contractor |  | 3% |  | 675 |  | 20.25 | 114.75 |  | 810
Name: |  | 0% |  | 0 |  | 0 | 0 |  | 0
[9 empty] | Subs' Total | 2937.758
(Attach: Separate Contract Change Detailed Breakdown for each Subcontractor | [8 empty] | Total | 4727.558
Time Extension Justification, if applicable) |  |  |  |  | Time Extension: | 0 | Work Days | Bond% | 2% | 94.5512
*See General Conditions, Article 4.1.D for allowed Overhead and Profit percentages. | [8 empty] | GRAND TOTAL | 4822.1092

## SUB Detailed Breakdown
Contract Change Detailed Breakdown |  |  |  | Subcontractor Name: |  | Union Electric |  |  | SUBCONTRACTOR | SUB-SUBCONTRACTOR
State's Project No. | X0000-00 | Description of Change: | [6 empty] | Sheet | 2 of 3
Proposal No. | 1 | Add (3) new conduits. | [6 empty] | Prepared By: | Rep's Name of SUB
Date | mm/dd/yy | [7 empty] | Signed By: | Rep of SUB
|  |  |  | LABOR |  | MATERIAL |  | EQUIPMENT / OTHER
WORK ITEM |  | QTY | UNIT | Unit Cost | Total | Unit Cost | Total | Unit Cost | Total | SUBTOTAL | REVISIONS
(3) 2" conduit for future use for phone |  | 20 | hours | 75 | 1500 |  |  |  |  | 1500
2" conduit |  | 36 | lf |  |  | 8.85 | 318.6 |  |  | 318.6
Total Direct Costs |  |  |  |  | 1500 |  | 318.6 |  | 0 | 1818.6
Overhead & Profit |  | 14% | *OH&P% |  | 210 |  | 44.604 |  | 0 | 254.604
[9 empty] | Subcontractor's Total | 2073.204
SUB-SUBCONTRACT COSTS
SUB-SUBCONTRACTOR |  | *Sub OH&P% |  | Sub-Sub Total Direct Costs |  | *Sub OH&P | *Sub-Sub OH&P |  | Total
Name: Sub-SUB Coring Contractor |  | 3% |  | 675 |  | 20.25 | 94.5 |  | 789.75
Name: |  | 0% |  | 0 |  | 0 | 0 |  | 0
Name: |  | 0% |  | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub-Sub's Total | 789.75
(Attach separate Contract Change Detailed Breakdown for each Sub-Subcontractor) | [8 empty] | GRAND TOTAL | 2862.954
*See General Conditions, Article 4.1.D for allowed Overhead and Profit percentages.

## SUB-SUB Detailed Breakdown
Contract Change Detailed Breakdown |  |  |  | Subcontractor Name: |  | Coring Contractor |  |  | SUBCONTRACTOR | SUB-SUBCONTRACTOR
State's Project No. | X0000-00 | Description of Change: | [6 empty] | Sheet | 3 of 3
Proposal No. | 1 | To core holes for piping and to patch for SAMPLE PROJECT. | [6 empty] | Prepared By: | Rep's Name of Sub-SUB
Date | mm/dd/yy | [7 empty] | Signed By: | Rep of Sub-SUB
|  |  |  | LABOR |  | MATERIAL |  | EQUIPMENT / OTHER
WORK ITEM |  | QTY | UNIT | Unit Cost | Total | Unit Cost | Total | Unit Cost | Total | SUBTOTAL | REVISIONS
Core 3 - 4" holes |  | 3 | each |  |  |  |  | 150 | 450 | 450
Patch surface and other holes in same area |  | 3 |  | 55 | 165 | 20 | 60 |  |  | 225
Total Direct Costs |  |  |  |  | 165 |  | 60 |  | 450 | 675
Overhead & Profit |  | 14% | *OH&P% |  | 23.1 |  | 8.4 |  | 63 | 94.5
[9 empty] | Subcontractor's Total | 769.5
SUB-SUBCONTRACT COSTS
SUB-SUBCONTRACTOR |  | *Sub OH&P% |  | Sub-Sub Total Direct Costs |  | *Sub OH&P | *Sub-Sub OH&P |  | Total
Name: |  | 0% |  | 0 |  | 0 | 0 |  | 0
Name: |  | 0% |  | 0 |  | 0 | 0 |  | 0
Name: |  | 0% |  | 0 |  | 0 | 0 |  | 0
[9 empty] | Sub-Sub's Total | 0
(Attach separate Contract Change Detailed Breakdown for each Sub-Subcontractor) | [8 empty] | GRAND TOTAL | 769.5
*See General Conditions, Article 4.1.D for allowed Overhead and Profit percentages.

## Proposal Summary (hidden)
Change Order Proposal Summary |  |  |  | Prime Contractor:
State's Contract No. |  | Contract Title/Location |  |  |  |  | Date
Description of Change | [6 empty] | Estimate No.
|  |  | Second Tier Sub Work |  |  |  | Revision
| Sub-subcontractor |  |  | $
| Sub-subcontractor |  |  | $
1 | Direct Cost Subtotal |  |  |  | $
2 | Overhead & Profit on direct costs (Line 1) |  |  | % | $
3 | Subtotal |  |  |  |  | $
Subcontractor's Work
| Subcontractor |  |  | $
| Subcontractor |  |  | $
| Subcontractor |  |  | $
| Subcontractor |  |  | $
4 | Direct Cost Subtotal |  |  |  | $
5 | Overhead & Profit on direct costs (Line 4) |  |  | % | $
6 | Sub's Overhead & Profit on Tier Sub (Line 3) |  |  | % | $
7 | Subtotal |  |  |  |  | $
Prime Contractor's Work
8 | Direct Cost |  |  |  | $
9 | Overhead & Profit on Line 8 |  |  | % | $
10 | Prime's Overhead & Profit on Sub (Line 7) |  |  | % | $
11 | Prime's Overhead & Profit on Tier Sub (Line 3) |  |  | % | $
12 | Contract Unit Price Work |  |  |  | $
13 | Subtotal (Lines 8-12) |  |  |  |  | $
14 | TOTAL (Lines 3, 7, & 13) |  |  |  |  | $
15 | Bond & Insurance |  |  | % |  | $
|  |  | Change Order Total |  |  | $ | $
Time Extension |  | Work Days |  | Contractor's Signature
Attach: Detailed Estimates
Time Extension justification, if applicable