Copyright September 2012, Division of Facilities Management, Design and Construction (FMDC)

SECTION 013100 – COORDINATION

GENERAL

RELATED DOCUMENTS

Drawings and general provisions of the Contract including General and Supplementary Conditions and other Division 1 Specification Sections apply to this Section.

SUMMARY

This Section includes administrative provisions for coordinating construction operations on Projects including, but not limited to, the following:

Adjust list below to suit Project.

Coordination Drawings.

Administrative and supervisory personnel.

Project meetings.

Delete first paragraph below for projects conducted under a general construction contract.  If retaining paragraph for a project using multiple contracts, revise to suit local laws and regulations.  Some states and certain county and municipal jurisdictions prohibit assigning responsibility for coordination on a construction project to any Contractor involved in Project.  This usually forces Owner, who is often the jurisdiction itself, or Designer, into construction management activities.  Coordinate with Division 01 Section "Multiple Contract Summary".

Each Contractor shall participate in coordination requirements.  Certain areas of responsibility will be assigned to a specific Contractor.

Related Sections include the following:

List below only procedures that the reader might expect to find in this Section but are specified elsewhere.

Division 1, Section 013200 "Schedules" for preparing and submitting Contractor's Construction Schedule.

Articles 1.8.B and 1.8.C of Section 007213 "General Conditions" for coordinating meetings onsite.

Article 5.4.H of Section 007213 "General Conditions" for coordinating Closeout of the Contract.

COORDINATION

Requirements in this Article expand requirements in the General Conditions.  Delete if the General Conditions suit Project requirements and specific actions required.

Coordination:  Coordinate construction operations included in different Sections of the Specifications to ensure efficient and orderly installation of each part of the Work.  Coordinate construction operations included in different Sections, which depend on each other for proper installation, connection, and operation.

Retain paragraph above for work performed under a single contract.  Retain first paragraph below for work performed under multiple contracts.  Coordinate with Division 1, Section "Multiple Contract Summary".

Coordination:  Each Contractor shall coordinate its construction operations with those of other contractors and entities to ensure efficient and orderly installation of each part of the Work.  Each Contractor shall coordinate its operations with operations included in different Sections that depend on each other for proper installation, connection, and operation.

Retain subparagraphs below with either paragraph selected above.

Schedule construction operations in sequence required to obtain the best results where installation of one part of the Work depends on installation of other components, before or after its own installation.

Coordinate installation of different components with other Contractors to ensure maximum accessibility for required maintenance, service, and repair.

Make adequate provisions to accommodate items scheduled for later installation.

Where availability of space is limited, coordinate installation of different components to ensure maximum performance and accessibility for required maintenance, service, and repair of all components including mechanical and electrical.

Prepare memoranda for distribution to each party involved outlining special procedures required for coordination.  Include such items as required notices, reports, and list of attendees at meetings.

Prepare similar memoranda for Owner and separate Contractors if coordination of their Work is required.

Administrative Procedures:  Coordinate scheduling and timing of required administrative procedures with other construction activities and activities of other Contractors to avoid conflicts and to ensure orderly progress of the Work.  Such administrative activities include, but are not limited to, the following:

Insert other administrative activities below to suit Project.

Preparation of Contractor's Construction Schedule.

Preparation of the Schedule of Values.

Installation and removal of temporary facilities and controls.

Delivery and processing of submittals.

Progress meetings.

Preinstallation conferences.

Startup and adjustment of systems.

Project Closeout activities.

Conservation provisions in paragraph below may be difficult to enforce.  Penalties for wasteful practices, if necessary, are more enforceable if made a condition of the Contract and added by Supplementary Conditions.  Insert specific conservation requirements in appropriate Sections.

Conservation:  Coordinate construction activities to ensure that operations are carried out with consideration given to conservation of energy, water, and materials.

Salvage materials and equipment involved in performance of, but not actually incorporated into, the Work.  Refer to other Sections for disposition of salvaged materials that are designated as Owner's property.

SUBMITTALS

Delete requirement for Coordination Drawings below if installation is completely shown on Shop Drawings.  Coordinate with individual Sections.

Coordination Drawings:  Prepare Coordination Drawings if limited space availability necessitates maximum utilization of space for efficient installation of different components or if coordination is required for installation of products and materials fabricated by separate entities.

Delete requirement in paragraph below for small projects.

Key Personnel Names:  Within fifteen (15) work days of starting construction operations, submit a list of key personnel assignments including superintendent and other personnel in attendance at Project site.  Identify individuals and their duties and responsibilities; list addresses and telephone numbers including home and office telephone numbers.  Provide names, addresses, and telephone numbers of individuals assigned as standbys in the absence of individuals assigned to Project.

Post copies of list in Project meeting room, in temporary field office, and by each temporary telephone.  Keep list current at all times.

Insert special requirements that exceed requirements contained in the General and Supplementary Conditions for Superintendent and assistants.

PROJECT MEETINGS

The Owner’s Construction Representative will schedule a Pre-Construction Meeting prior to beginning of construction.  The date, time, and exact place of this meeting will be determined after Contract Award and notification of all interested parties.  The Contractor shall arrange to have the Job Superintendent and all prime Subcontractors present at the meeting.  During the Pre-Construction Meeting, the construction procedures and information necessary for submitting payment requests will be discussed and materials distributed along with any other pertinent information.

Delete paragraph and subparagraphs below if a Pre-Construction Meeting is not required.  If required, adjust number of days to suit Project.

Add items to list below to suit Project.

Minutes:  Designer will record and distribute meeting minutes.

Progress Meetings:  The Owner’s Construction Representative will conduct Monthly Progress Meetings as stated in Articles 1.8.B and 1.8.C of Section 007213 “General Conditions”.

Minutes:  Designer will record and distribute to Contractor the meeting minutes.

Delete paragraph and subparagraphs below if Project does not require preinstallation conferences.  Limit preinstallation conferences to major assemblies if the Work requires tight control and coordination.  If necessary, individual Sections should specify preinstallation conferences as a requirement and should reference this Section.

Preinstallation Conferences:  Contractor shall conduct a preinstallation conference at Project site before each construction activity that requires coordination with other construction.

Attendees:  Installer and representatives of Manufacturers and Fabricators involved in or affected by the installation and its coordination or integration with other materials and installations that have preceded or will follow, shall attend the meeting.  Advise Designer and Construction Representative of scheduled meeting dates.

Agenda:  Review progress of other construction activities and preparations for the particular activity under consideration including requirements for the following:

Delete unnecessary items from list below.  Add items to suit Project.

Contract Documents

Options

Related RFIs

Related Change Orders

Purchases

Deliveries

Submittals

Review of mockups

Possible conflicts

Compatibility problems

Time schedules

Weather limitations

Manufacturer's written recommendations

Warranty requirements

Compatibility of materials

Acceptability of substrates

Temporary facilities and controls

Space and access limitations

Regulations of authorities having jurisdiction

Testing and inspecting requirements

Installation procedures

Coordination with other Work

Required performance results

Protection of adjacent Work

Protection of construction and personnel

Contractor shall record significant conference discussions, agreements, and disagreements including required corrective measures and actions.

Reporting:  Distribute minutes of the meeting to each party present and to parties who should have been present.

Do not proceed with installation if the conference cannot be successfully concluded.  Initiate whatever actions are necessary to resolve impediments to performance of the Work and reconvene the conference at earliest feasible date.

Revise paragraph below if Project requires holding progress meetings at different intervals.  Insert special intervals such as "every third Tuesday" to suit special circumstances.

Paragraph and subparagraphs below are usually deleted, except for multiple contracts, because they are not needed.  Retain if Project is constructed under multiple contracts or if some unusual circumstance requires tighter control than normal.  Under multiple contracts, Owner often assigns responsibility for scheduling and conducting meetings to Project Coordinator.  Insert special intervals such as "every third Tuesday" to suit special circumstances.

If special meetings such as site mobilization conferences or Project Closeout conferences are required, insert articles here specifying meeting requirements.

Project name

Name and address of Contractor

Name and address of Designer

RFI number including RFIs that were dropped and not submitted

RFI description

Date the RFI was submitted

Date Designer's response was received

Identification of related DSI or Proposal Request, as appropriate

PRODUCTS (Not Used)

EXECUTION (Not Used)

END OF SECTION  013100