## FORM A
STATE OF MISSOURI
|  | OFFICE OF ADMINISTRATION | [11 empty] | A
|  | DIVISION OF FACILITIES MANAGEMENT, DESIGN AND CONSTRUCTION | [7 empty] | PROJECT NUMBER
APPLICATION AND CERTIFICATION FOR PAYMENT - FORM A
INSTRUCTIONS ON PAGE 2 | [8 empty] | PROJECT TITLE
CONTRACTOR | [8 empty] | LOCATION
FIRM | [8 empty] | APPLICATION NUMBER |  | FROM |  | TO
ADDRESS | [8 empty] | DESIGNER
CITY | [5 empty] | STATE |  | ZIP | FIRM
CONTRACTOR'S APPLICATION FOR PAYMENT | [8 empty] | ADDRESS
Application is made for Payment as shown below in connection with the Contract Continuation Sheets | [8 empty] | CITY |  | STATE |  | ZIP
attached (if applicable), Form B and Form C. | [8 empty] | In accordance with the Contract Documents based on site observations and the data comprising the above Application, the Designer certifies to the Owner that, to the best of the Designer's knowledge, the information and belief the Work has progressed as indicated, the quality of the Work in accordance with the Contract Documents, and the Contractor is entitled to payment of the amount certified.
1. ORIGINAL CONTRACT SUM | [5 empty] | $
2. Net by Contract Change # |  |  | ______ | through _________ |  | $
3. TOTAL Contract sum to date (Line 1 + 2) | [5 empty] | $ | 0
4. **TOTAL completed and stored to date (Col. G on Sheet B) | [5 empty] | $
5. Retainage: 5% of Line 4 above | [5 empty] | $
6. Total earned less Retainage (Line 4 less Line 5 total) | [5 empty] | $ | 0 |  | LESS ITEMS IN ARTICLE 5.4-H.5 OF THE GENERAL CONDITIONS
7. Less previous Applications for Payments | [5 empty] | $ |  |  | AMOUNT CERTIFIED
8. Current Payment Due | [5 empty] | $ | 0 |  | (ATTACH EXPLANATION IF AMOUNT CERTIFIED DIFFERS FROM APPLICATION AMOUNT)
The Contractor hereby certifies, to the best of the Contractor's knowledge, the Work covered by the Application for Payment has been completed in accordance with the Contract Documents, all amounts have been paid by the Contractor for Work for which previous Applications for Payment were issued and payments received from Owner, current payment shown herein is now due, the Construction Schedule has been updated and accurately reflects the Work completed to date for which payment is requested, and the remaining Work and time required to complete the project. | [8 empty] | DESIGNER'S CERTIFICATION
[9 empty] | SIGNATURE |  |  | DATE
APPROVAL RECOMMENDED: OWNER'S CONSTRUCTION REPRESENTATIOVE
[9 empty] | SIGNATURE |  |  | DATE
APPROVAL RECOMMENDED: PROJECT MANAGEMENT UNIT
[9 empty] | SIGNATURE |  |  | DATE
FISCAL AUDIT & ENTRY: CI FISCAL ACCOUNTANT
[9 empty] | SIGNATURE |  |  | DATE
CONTRACTOR | [8 empty] | APPROVED FOR PAYMENT: CI FISCAL SUPERVISOR
BY | [5 empty] | DATE |  |  | SIGNATURE |  |  | DATE
Revised 4/17 |  |  |  |  | ORIGINAL: FILE/Contractor Payments
INSTRUCTIONS FOR APPLICATION AND CERTIFICATION FOR PAYMENT FORM A
The Division of Facilities Management, Design and Construction standard APPLICATION AND CERTIFICATION FOR PAYMENT consists of three (3) Forms - A, B, and C.
The forms and instructions for completion and submittal are provided to the Contractor for his use in applying for payments as provided in Article 5.4 of the Contract General Conditions. Detailed instructions for completing the forms appear below.
The SUMMARY AND SIGNATURE DOCUMENT - A provides the project identification, fiscal summary, and spaces for required signatures necessary for processing and payment. Completion of A is required for payment application on all projects. Application for Payment on a project on which a single billing will be made may be accomplished using A by completing the information section and items 1,2,3,4,6, and 8 of the fiscal summary.
Project on which applications for partial payments are being made require completion of Form B - CONTRACT BREAKDOWN AND EXTENSIONS.
Application for Payment, which includes materials stored on-site, requires the completion and submission of Form C - STORED MATERIAL BREAKDOWN.
Sample forms of each will be provided to the Contractor at the time the Notice to Proceed is issued. The Contractor will be expected to reproduce additional copies of each form as required to provide a minimum of four (4) sets (or as established during the Pre-Construction Meeting) to the Designer for review and certification.
The Owner will make payment directly to the Contractor based on the amount certified by the Designer and approved by the designated Officials.
The final Application for Payment should be identified as the final request and include the following:
MBE/WBE/SDVE Report
Final Receipt and Payment Releases
Affidavits - Compliance with Prevailing Wage
Warranties and Guarantees
Certified Copy of Contractor Payrolls
Red-Line Record Drawings

## FORM B
| STATE OF MISSOURI |  |  |  |  | PROJECT NUMBER | APPLICATION NUMBER |  | B
OFFICE OF ADMINISTRATION
| DIVISION OF FACILITIES MANAGEMENT, DESIGN AND CONSTRUCTION |  |  |  |  | PAGE OF | DATE
| CONTRACT BREAKDOWN AND EXTENSIONS - FORM B | [5 empty] | TO
INSTRUCTIONS ON PAGE 3
A | B | C | D | E | F | G |  | H | I
COMPLETED
|  |  | FROM PREVIOUS APPLICATION D & E |  | MATERIALS PRESENTLY STORED (from FORM C) | TOTAL COMPLETED AND STORED TO DATE D + E + F | % | BALANCE TO FINISH C - G
ITEM |  | SCHEDULED |  | THIS APPLICATION |  |  | G ÷ C |  | REMARKS
NO. | DESCRIPTION OF WORK | VALUE
1 | [5 empty] | 0
2 | [5 empty] | 0 |  |  |  | 0
3 | [5 empty] | 0
4 | [5 empty] | 0
5 | [5 empty] | 0
6 | [5 empty] | 0
7 | [5 empty] | 0
8 | [5 empty] | 0
9 | [5 empty] | 0
10 | [5 empty] | 0
11 | [5 empty] | 0
12 | [5 empty] | 0
13 | [5 empty] | 0
14 | [5 empty] | 0
15 | [5 empty] | 0
16 | [5 empty] | 0
17 | [5 empty] | 0
18 | [5 empty] | 0
19 | [5 empty] | 0
20 | [5 empty] | 0
21 | [5 empty] | 0
| PAGE TOTAL | 0 | 0 | 0 | 0 | 0 |  | 0
| GRAND TOTAL | 0 | 0 | 0 | 0 | 0 |  | 0
TO BE ATTACHED TO APPLICATION AND CERTIFICATION FOR PAYMENT, FORM A | [5 empty] | ADAPTED FROM A/A/G-702-1983
Revised 4/17 |  |  | ORIGINAL: FILE/Contractor Payments
| STATE OF MISSOURI |  |  |  |  | PROJECT NUMBER | APPLICATION NUMBER |  | B
OFFICE OF ADMINISTRATION
| DIVISION OF FACILITIES MANAGEMENT, DESIGN AND CONSTRUCTION |  |  |  |  | PAGE OF | DATE
| CONTRACT BREAKDOWN AND EXTENSIONS - FORM B | [5 empty] | TO
INSTRUCTIONS ON PAGE 3
A | B | C | D | E | F | G |  | H | I
COMPLETED
|  |  | FROM PREVIOUS APPLICATION D & E |  | MATERIALS PRESENTLY STORED (from FORM C) | TOTAL COMPLETED AND STORED TO DATE D + E + F | % | BALANCE TO FINISH C - G
ITEM |  | SCHEDULED |  | THIS APPLICATION |  |  | G ÷ C |  | REMARKS
NO. | DESCRIPTION OF WORK | VALUE
22 | [5 empty] | 0
23 | [5 empty] | 0
24 | [5 empty] | 0
25 | [5 empty] | 0
26 | [5 empty] | 0
27 | [5 empty] | 0
28 | [5 empty] | 0
29 | [5 empty] | 0
30 | [5 empty] | 0
31 | [5 empty] | 0
32 | [5 empty] | 0
33 | [5 empty] | 0
34 | [5 empty] | 0
35 | [5 empty] | 0
36 | [5 empty] | 0
37 | [5 empty] | 0
38 | [5 empty] | 0
39 | [5 empty] | 0
40 | [5 empty] | 0
41 | [5 empty] | 0
42 | [5 empty] | 0
| PAGE TOTAL | 0 | 0 | 0 | 0 | 0 |  | 0
| GRAND TOTAL | 0 | 0 | 0 | 0 | 0 |  | 0
TO BE ATTACHED TO APPLICATION AND CERTIFICATION FOR PAYMENT, FORM A | [5 empty] | ADAPTED FROM A/A/G-702-1983
Revised 4/17 |  |  | ORIGINAL: FILE/Contractor Payments
INSTRUCTIONS FOR CONTRACT BREAKDOWN AND EXTENSION PREPARATION FORM B
** PLEASE BEGIN TYPING ON NUMBER 1 (COLUMN B, DESCRIPTION OF WORK)
Heading: Complete the information here consistent with similar information on FMDC Document Form A - Application and Certification for Payment.
Columns A, B, & C: These Columns should be completed by identifying the various portions of the project and their scheduled value consistent with the Schedule of Value consistent with the Schedule of Values submitted to and approved by the Designer at the commencement of the Project. The breakdown may be by Sections of the Work or by Subcontractors and shall remain consistent throughout the Project. Multiple pages should be used when required.
Column C: Must be subtotaled at the bottom when more than one (1) page is used and totaled on the last page. Initially, this total must equal the Original Contract Amount. The total of Column C will only be adjusted by Contract Change during the Project.
Column D: Enter in this Column the amount of completed Work covered by the previous Application. This is the total of Columns D and E from the previous Application. Values from Column F (Materials Presently Stored) from prior payments should not be entered in this Column.
Column E: Enter here the value of Work completed this Application period including the value of materials incorporated in the Project which were listed on the previous Application and Certification for Payment under Materials Presently Stored (Column F).
Column F: Enter here the value of Materials Presently Stored and itemized on Form C on which payment is sought. The total of the Column must be recalculated at the end of each pay period. This value covers both materials newly stored for which payment is sought and materials previously stored which are not yet incorporated in the Project. Payment by the Owner for stored materials does not in itself result in a deduction from this Column. Only as materials are incorporated into the Project is their value deducted from this Column and incorporated into Column E (Work Completed - This Period).
Column G: Enter here the total of Columns D, E, and F. Calculate the percentage completed by dividing Column G by Column D.
Column H: Enter here the difference between Column C (Scheduled Value) and Column G (Total Completed and Stored to Date).
Column I: Space reserved for notations or comments by Designer or Construction Representative.
PAGE 3

## FORM C
| STATE OF MISSOURI |  |  |  |  | PROJECT NUMBER | APPLICATION NUMBER |  | C
OFFICE OF ADMINISTRATION
| DIVISION OF FACILITIES MANAGEMENT, DESIGN AND CONSTRUCTION |  |  |  |  | PAGE OF | DATE
| STORED MATERIAL BREAKDOWN - FORM C | [5 empty] | TO
INSTRUCTIONS ON PAGE 2
A | B | C | D | E | F | G |  | H | I
|  |  | QUANTITY |  |  |  |  | EXTENSION
| ITEM |  | REMAINING IN | QUANTITY |  |  |  | VALUE | MATERIAL
ITEM | NO. | MATERIAL DESCRIPTION | STORAGE FROM | ADDED | TOTAL | UNIT OF | UNIT | (TO BE | ON/OFFSITE
NO. | FROM |  | PREVIOUS | THIS | D + E | MEASURE | VALUE | FORWARDED | LOCATION
| FORM |  | APPLICATIONS | APPLICATION |  |  |  | TO
| B | [6 empty] | FORM B
COLUMN F)
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
[5 empty] | 0 |  |  | 0
Revised 4/17 |  |  | ORIGINAL: FILE/Contractor Payments
INFORMATION/INSTRUCTIONS FOR STORED MATERIAL BREAKDOWN FORM C
The Stored Material Breakdown Form provides quantity and value information regarding Materials Stored on/off the jobsite, but not yet incorporated into the Work in accordance with revisions specified in the Contract General Conditions shown below.
Materials Stored On/Offsite of Work and not yet incorporated in Work, if suitably stored, will be allowed in the Application and Certification
for Payment on the basis of one hundred (100%) percent of value providing:
1. | Material has previously been approved through submittal and acceptance of shop drawings conforming to requirements of Article
3.2 of the General Conditions.
2. | Delivery is made in accordance with the timeframe on the Approved Schedule.
3. | Materials, equipment, etc., are properly stored and protected from damage and deterioration and remain so -- if not, previously
approved amount will be deleted from subsequent Pay Applications.
4. | The payment request is accompanied by an invoice identifying the material, equipment, etc., in sufficient detail to establish
quantity and value.
PREPARATION:
PROJECT NUMBER, APPLICATION NUMBER, AND DATE -- Enter information consistent with similar entries shown on Form A.
ITEM NUMBER - Consecutive Numbering
ITEM NUMBERING from Form B - Enter the Item Number from the Contract Breakdown and Extension Form from which the material
was shown in Column F.
MATERIAL DESCRIPTION - Briefly describe for identification the material or equipment stored.
QUANTITY REMAINING IN STORAGE FROM PREVIOUS APPLICATIONS - Enter the number of units remaining in storage from
previous Application(s).
QUANTITY ADDED THIS APPLICATION - Enter the number of units added this Application.
TOTAL - Enter the total of Columns D and E.
UNIT OF MEASURE - Enter the unit of measure, i.e., SF (square feet), SY (square yards), EA (each), T (tons), etc..
EXTENSION VALUE - F x G - Enter total value to be forwarded to Contract Breakdown and Extension, Form B, Item F.
MATERIAL STORAGE ON/OFFSITE LOCATION - Briefly describe the storage location by room number, trailer identification or area
of site, or (if offsite) attach approved Offsite Storage of Materials Request Form.
PAGE 2