## Vehicle Information
Vehicle Information (For the initial request, complete columns A through I)
Asset List, install locations, hardware details
Billing Account | Telematics Group | Vehicle Description | VIN | Year | Make | Model | Go Device | Harnesses Required | Odometer (time of install) | Verify Go Device Firmware | Verfy Link with Geotab | Install Location | Installer Contact Name | Installer Cell Number

## Sheet1 (hidden)
Reference | Type
(blank) | (blank)
(blank) Total
Grand Total

## Project Installation Schedule (hidden)
Installation Schedule
[6 empty] | Week 1 |  |  |  |  | Week 2
| Location Branch | Installer | Percent Complete | Number of Actual Vehicles Complete | Number of Planned Vehicles | 2014-07-14 | 2014-07-15 | 2014-07-16 | 2014-07-17 | 2014-07-18 | 2014-07-21 | 2014-07-22 | 2014-07-23 | 2014-07-24 | 2014-07-25
[6 empty] | Mon | Tues | Wed | Thurs | Fri | Mon | Tues | Wed | Thurs | Fri
| Orlando | Installer 1 | 100% | 58 | 58 | 2014-07-14: 14; 2014-07-15: 10; 2014-07-16: 12; 2014-07-17: 12; 2014-07-18: 10
| Michigan | Installer 2 | 100% | 54 | 54 | 2014-07-14: 10; 2014-07-15: 12; 2014-07-16: 12; 2014-07-17: 10; 2014-07-18: 10
| Tallahassee | Installer 1 | 100% | 25 | 25 | 2014-07-21: 12; 2014-07-22: 13; 2014-07-23: Travel day
| Montgomery | Installer 1 | 50% | 10 | 20 | 2014-07-24: 10; 2014-07-25: 10
| Chicago | Installer 2 | 100% | 8 | 8 | 2014-07-21: 8; 2014-07-22: Travel day
| Indianapolis | Installer 2 | 90% | 27 | 30 | 2014-07-23: 13; 2014-07-24: 12; 2014-07-25: 5
| xxx | xxx | xxx | xxx | xxx
| xxx | xxx | xxx | xxx | xxx
| xxx | xxx | xxx | xxx | xxx
| xxx | xxx | xxx | xxx | xxx
| xxx | xxx | xxx | xxx | xxx
Total # of Vehicles |  |  |  | xxx | 800
Legend
Completed
Partial Completion
Not Completed